# Oregon Joint Use Association

Publicity and Education Committee

Meeting Minutes – December 13, 2012

# Call to Order

Meeting called to order by Jerry at 10:04am.

Present  - Steve Ross, Jerry Donovan, Ian Scott, Colin Cavasher, Tom Jorgenson, Dawna Farrell.  Jeff VanLoo not able to attend due to road conditions.

# Approval of Minutes

Review minutes of November 15, 2012 – Motion, 1st by Colin,

2nd by Ian, accepted as submitted, with changes.

With changes as follow: Change in categories – Ian will be doing Building Verticals – not Colin.

Standing Meeting Schedule – discussed a committee form that is being worked on that will include commitments, responsibilities and provide a document for committee members and their management so that employers are aware that this participation is an honor and needs the support of the managers to be involved.  One portion of the committee form will include suggested meeting dates so committee members can plan ahead and make every effort to attend all events if possible.

P & E Committee, 10 am – noon, 1st Thursday (unless otherwise noted)

January 10

February 7

March 7

April 4

May 2

June 13

July 11

August 1

September 5

October 3

November 14

December 5

Discussed dates, at this time these dates look acceptable to the committee and discussed including the goal of placing specific weeks for annual meeting and spring training to include in the committee report.

Save the Date: passed out draft of save the date flyer for committee to review and provide input before finalizing and sending out to members and others that apply- discussed changes, staff to make updates and send out for one more review before e-blast.  Also need to get approved flyer on website.

2013 Spring Training

- Discuss determining “standing date” to facilitate locking in speakers and setting training agenda, etc. – Previously discussed with committee meeting dates.

- Continue discussion on development of Spring Event Agenda: Group agreed on the following information to be sent to Dave Marne to assist with his presentation set up.

- Session to assist field workers in understanding the terminology the engineers

use, building better formats for communication.

- Clearing up misconceptions within the industry “myth busters”/”tall tales” sort of segment; such as a Cedar poles being stronger than a Douglas Fir poles.

- New pictures to go along with Dave Marne’s presentation.

- Lockdown of Jeopardy categories, questions and collection of photos:

(Jeff wants to work on all categories.)

- Grandfathering – group discussed varying opinions on this category – some want to keep, some think it is a Pandora’s Box of issues.  Group discussed asking Marne to discuss grandfathering rather than include it in the Jeopardy game.  Final decision was to eliminate grandfathering from game and not ask Marne to discuss at this time.  He briefly touches on this already.

- Mid Span Issues – Vertical & Horizontal – Dawna

- Violations at pole - Steve

- Building Verticals – Ian

- Service Ends – Tom

- Grounding – Jerry

Colin requested if possible, best way to get photos and questions to him are by USB or CD rather than email due to size and issues last year with strain on his email account.

What is needed for the game – 1-2 photos to go with one question, 1-3 wrong answers, 1 right answer, the rule & page # in NESC Code Book.  5 of these for each category.

- Confirm - Last meeting committee decided to go the direction of determining what codes they want to bring to light and then each go out and obtain photos that work correctly with the code and then build the game.

Already discussed – no tricks in the game.

- Status - Colin is working on software to figure out how to display names along with the # of the persons/clicker.

Colin is working on figuring out how to make clickers identify tables more easily so the game will move smoother, in progress.

- Confirm - Colin will be able to attend 2013 Spring Training?

Still not sure if he can attend.  Jerry and Colin to discuss further.

- Spring Training Timeline:

Task						Target Date

Speaker(s) recommendation to Board		August 1

Lockdown of Speaker(s)			September 1

Lockdown of Categories			November 1, 2012

Electronic save-the-date flyer distributed		November 15, 2012

Waiting on final approval but will be out shortly.

Lockdown of Agenda 				December 15, 2012

Staff to get draft agenda to Jerry by middle of next week.

Deadline for photos to Colin/Committee		January 4, 2013

Questions to Colin/Committee			January 4, 2013

Draft Registration form due 			January 10, 2013

Registration form out 				January 15, 2013

Monthly e-blast reminder about training through March 15

Finalize Question/Photos			February 1, 2013

Draft of game completed 			March 1, 2013

Final facility inspection & walk-through		March 1, 2013

Weekly e-blast reminder about training starting after March 15

Game completed and tested			March 23, 2013

Focus on logistics				March 23 – April 23, 2013

Follow-up on Open Action Items

- Committee Structure Document – Jerry

- Mission Statement – Jerry working on draft form

- Committee makeup (adding members from under-represented sectors)

- Expectations for P&E committee members (number of meetings, etc.)

- Minimum length of term – suggested 2 year minimum

- Attendance at Annual Meeting, Spring Training, etc.

- Current committee assistance requested in creating a bullet point list of reasons that employers should allow and encourage their employees to participate on the committee.

  - Nothing added at this time, Jerry welcomes suggestions when the draft is sent out.

- Committee makeup (adding members from under-represented sectors) – Jerry requested that committee come directly to him with some names/who they work for, open up some discussion of potential new members.

  - Jerry asked committee members to consider new potential members including a possible government representative and construction lineman.  Bring suggestions.  Steve suggested an open house with a presentation about what the committee is about and what it takes to get on the committee.  Not everyone gets to be on the committee, but have to benefit the committee’s mission.

Other Business

Discussed and revised timeline to include registration draft and e-blasts.

Next Meeting

When – Jan. 10, 2013

Where – Comcast in Beaverton?

Time – 10am – 12pm

#### Adjourn

Meeting adjourned at 11:32am.